## Sheet1
Admission management system	Date
1.database wire frame preparation	04/05/19
2.database script preparation	06/05/19
3.database review exception	07/05/19
4.Abstract document preparation	07/05/19
5.project baseline set up	07/05/19
6.project – maven integration with dependencies	07/05/19
7.project – identify the business objects	07/05/19
8.project – display menu items	07/05/19
9.Adding – column modules	08/05/19
---- login servlet	08/05/19
---- payment serv	08/05/19
---- utilities	08/05/19
10.project – validation implementation(ui layer)	08/05/19
11.project – dao implementation	08/05/19
12.servlet/implementation controller	09/05/19
13.service/business implementation	09/05/19
14.feature wise -> DAO implementation	10/05/19
15.utilities common functionality implementation	10/05/19
16.Javascript session part – 1	14/05/19
17.project updates	14/05/19
18.Agile introduction	14/05/19
19.one to one discussion	14/05/19
20.SQL Batch Update- Sample	15/05/19
21.Junit Session	15/05/19
22.Log4j session	15/05/19
23.Utilities – External Utility API (String Utils, File Utils)	16/05/19
24.Convert Dynamic web -> Maven Project	16/05/19
25.Javascript ---page redirect	17/05/19
---dialog boxes	17/05/19
---html dom	17/05/19
----validations	17/05/19
26.one to one discussion	17/05/19
27.project demo 2nd review	17/05/19
28.assessment L2 & L3	17/05/19
29.scenario based questions - discussion	17/05/19
30.Jquery/ Js ajax (diff)	20/05/19
31.JDBC / gc/ arrays	20/05/19
32.web application configuration	20/05/19
33.Abstract document - Reviewed	21/05/19
34.Demo Project Review	21/05/19
35.Naming convention / coding standards	21/05/19
36.defined exceptions / joins / sub query	21/05/19
37.UI – validations / alignments / css	21/05/19
38.Final Project review	21/05/19
39.Demo to client
40.share source code / DB scipts – git repository